## Test case
Test case ID | Test case name | Precondition | Test steps | Expectation | Test status | Defect ID | Assumption/Note
TC-01 | Verify the search screen is properly visible and in proportion with UI | User is on Search screen | 1. Check the font size and font color of the text entered in the search box 2. Check the font size and font color of cities list 3. Verify display of cities list is center align | 1 | PASS |  | With the assumption that there is no interface difference between the actual app and the design
TC-02 | Validate the search box takes a maximum length of text for which it is designed | User is on Search screen | 1. Enter keyword that has the length = 51 characters 2. Check behavior of search box | 2. User is unable to enters into search box the keyword that has more than 50 characters | FAIL | Defect-01 | With the assumption that maxlength of search box is 50 character
TC-03 | Validate search rules defined for "Start with" the search key word | User is on Search screen | 1. Enter keyword that has value "Aban" 2. Check the search result | 2. Search result shows all cities that have the name start with "Aban" | PASS |  | Normally, searching feature allow to search with rule " contains" with search algorithm is "exact" or " similar". But in this case, my assumption is that function only allows to search the city that have the name "start with" keyword.
TC-04 | Validate search rules when keyword starts with space | User is on Search screen | 1. Enter keyword that has value " Baak" into search box 2. Check the search result | 2. Search result shows all cities have the name starts with "Baak" | FAIL | Defect-02
TC-05 | Validate search rules when keyword ends with space | User is on Search screen | 1. Enter keyword that has value "Abu " into search box 2. Check the search result | 2. Search result show all cities have the name starts with "Baak" | PASS | Defect-02
TC-06 | Validate search rules defined for "not case sensitive" | User is on Search screen | 1. Enter keyword that has value "a dos" 2. Check the search result | 2. Search result shows cities that are not case sensitive and contains string "a dos" - A Dos Cunhados, PT - A Dos Francos, PT - A dos Cunhados, PT | PASS
TC-07 | Validate search rules when have no result matchs the keyword | User is on Search screen | 1. Enter keyword "Vietnam" into search box 2. Check the search result | 2. There is a label in center of screen shows "No record found" | FAIL | Defect-03
TC-08 | Validate search result should be showed full records when user clears search box | User is on Search screen | 1. Enter keyword that has value "AElvkar" 2. Clear the keyword in search box 3. Check the search result | 2. Search result has full of record | FAIL | Defect-04
TC-09 | Verify pagination on search result | User is on Search screen | 1. Enter keyword "aba" into search box 2. Check the pagination of search result | 2. If the search result has more than 20 valid records, the screen will display the first 20 records and will load more when the user scrolls up. | PASS
TC-10 | Verify order of search result | User is on Search screen | 1. Enter keyword "aba" into search box 2. Check the order search result | 2. Search results are sorted alphabetically ASC | PASS
TC-11 | Verify user clicks on 1 city in search result | User is on Search screen | 1. Enter keyword "Abadan" into search box 2. Tap on search result "Abadan, IR" 3. Verify the city is display in google map | 3. User see the location of city in google map | FAIL | Defect-05
TC-12 | Verify when user clicks on any city from result and navigates back | User is on Search screen | 1. Enter keyword "Abadan" into search box 2. Tap on search result "Abadan, IR" 3. Press Back button from navigation panel of device | 3. Search result is maintained | PASS
TC-13 | Verify behavior of app when switching to another app | User is on Search screen | 1. Enter keyword "Abadan" into search box 2. Tap on search result "Abadan, IR" 3. Switching to other app 4. Swiching back to Mobile Assignment app | 3. Search result is maintained | PASS
TC-14 | Veri+F15+B14:H15 |  | 1. User copies the keyword "aban" from other plan 2. Tap on search box and paste value into box | 2.User can paste value normally and search result show values start with keyword | PASS

## Defects
Defect ID | Description | Platform version | Test Device | Steps to reproduce | Expected result | Actual result | Evidence | Priority | Severity | How to fix
Defect-01 | User can enter more than 50 characters into search box | Android 11 | Galaxy S21 | 1. Enter keyword that has the length = 51 characters 2. Check behavior of search box | 2. User is unable to enters into search box the keyword that has more than 50 characters | User can enter more than 50 characters | To be filled | Low | Low
Defect-02 | Search result didn't show when keyword starts with space character | Android 11 | Galaxy S21 | 1. Enter keyword that has value " Baak" or "Baak " into search box 2. Check the search result | 2. Search result shows all cities have the name starts with "Baak" | Search result is empty | To be filled | Low | Low | In class CityAdapter, line 67 , dd trim() method String filterString = charSequence.toString().toLowerCase().trim();
Defect-03 | App shows empty when have no result matchs the keyword | Android 11 | Galaxy S21 | 1. Enter keyword "Vietnam" into search box 2. Check the search result | 2. There is a label in center of screen shows "No record found" | Search result is empty | To be filled | Medium | Low
Defect-04 | App shows empty when user clears search box after entering the keyword that have no record found | Android 11 | Galaxy S21 | 1. Enter keyword that has value "123244354654756786879780890898" 2. Clear the keyword in search box by long press on Backspace button on keyboard 3. Check the search result | 2. Search result has full of records | Search result is empty or app show list of cities that are not relevant |  | High | Medium
Defect-05 | User can't see the location of city in google map | Android 11 | Galaxy S21 | 1. Enter keyword "Abadan" into search box 2. Tap on search result "Abadan, IR" 3. Verify the city is display in google map | 3. User see the location of city in google map | User can't see the location of city in google map | To be filled | High | Critical